Windows-First AI Agent Platform
Agile Development Blueprint

Product vision, architecture, epics, sprint roadmap, MVP and delivery model

# 1. Product Vision

Build a Windows-first AI Agent Builder that lets users create AI agents without writing code, connect local and cloud AI models, use tools, maintain memory, and execute useful workflows. The agent engine should remain independent from the UI so it can later support Android.

# 2. Target User Experience

User describes an agent → AI generates a workflow → user visually edits it → agent runs → model reasons → tools execute actions → memory stores/retrieves information → result is returned.

# 3. Recommended Technology Stack

Desktop: Tauri + React + TypeScript

Agent engine: Python + FastAPI initially

Database: SQLite

Vector memory: ChromaDB or LanceDB

Local AI runtime: Ollama

Workflow editor: React Flow

Cloud AI: provider adapters

File processing: Python

Version control: Git + GitHub

Packaging: Tauri Windows installer

# 4. High-Level Architecture

Windows UI (React/Tauri) → FastAPI → Agent Runtime → Model Router / Tool Manager / Memory Manager.

The Model Router supports local models through Ollama and cloud models through provider adapters. Local services provide SQLite, files, scheduling and notifications.

Core principle: the agent engine must not depend on a particular UI or AI provider.

# 5. Core Agent Components

Agent: identity, instructions, model, memory, tools, trigger and workflow.

Workflow: nodes and edges represented as JSON.

ExecutionContext: input, variables, node outputs, memory and metadata.

NodeExecutor: trigger, AI, tool, condition, loop, data and output execution.

ModelRouter: local, cloud or automatic model execution.

ToolManager: tools with schemas and permissions.

MemoryManager: conversation memory, saved facts and document/RAG memory.

# 6. Initial No-Code Node Library

Triggers: User Input, Schedule, File Added, Manual Run

AI: AI Model, Analyze, Summarize, Generate, Classify

Tools: Web Search, Read File, Write File, PDF Reader, Calculator

Logic: Condition, Loop, Switch, Wait

Memory/Data: Save Memory, Search Memory, Variable, Transform, Filter

Outputs: Message, Notification, Save File, API Response

# 7. Database MVP

agents — id, name, description, created_at, updated_at, status

workflows — id, agent_id, version, workflow_json, created_at

runs — id, agent_id, status, started_at, completed_at, input, output

run_steps — id, run_id, node_id, status, input, output, error

models — id, provider, name, type, status

tools — id, name, description, input_schema, output_schema, permission

memories — id, agent_id, type, content, metadata, created_at

settings — key, value

# 8. Agile Delivery Model

Use 2-week sprints. Each sprint has planning, development, integration/testing, bug fixing, review/demo and retrospective.

Agile board: BACKLOG → READY → IN PROGRESS → CODE REVIEW → TESTING → DONE.

Use P0/P1/P2/P3 priorities and story points for estimation.

# 9. Epic Roadmap

| Epic | Area | Sprints | Outcome |
| --- | --- | --- | --- |
| Epic 1 | Foundation | S1–S2 | Windows shell, React UI, FastAPI, SQLite, agent CRUD |
| Epic 2 | Local AI | S3–S4 | Ollama, local chat, model abstraction, cloud adapter |
| Epic 3 | Agent Engine | S5–S6 | Workflow runtime, execution context, logic, errors |
| Epic 4 | No-Code Builder | S7–S8 | React Flow editor, node library, persistence, execution |
| Epic 5 | Tools | S9–S10 | Core tools, PDF/web tools, AI tool calling, permissions |
| Epic 6 | Memory + RAG | S11 | Conversation memory, saved facts, document retrieval |
| Epic 7 | Autonomous Agents | S12 | Planning/action loop, limits and approvals |
| Epic 8 | Security + Product | S13–S16 | Security, offline mode, templates, QA, packaging |

# 10. Sprint Plan

## S1 — Foundation

Tasks: Windows app shell; React/Tauri; FastAPI /health; GitHub; navigation

Definition of Done: Runnable desktop shell

## S2 — Database + CRUD

Tasks: SQLite; core tables; agent CRUD APIs and UI

Definition of Done: Create/edit/delete/list agents

## S3 — Local AI

Tasks: Ollama; ModelService; /models and /chat; local chat UI

Definition of Done: Offline local chat

## S4 — Model Abstraction

Tasks: ModelProvider; Ollama provider; cloud adapter; model selection

Definition of Done: Switchable providers

## S5 — Agent Engine

Tasks: Workflow/Node/Edge/ExecutionContext; Trigger→AI→Output

Definition of Done: First executable agent

## S6 — Agent Engine v2

Tasks: Condition, tool, variable, loop, retries, timeouts, logs

Definition of Done: Reliable multi-step workflows

## S7 — Visual Builder

Tasks: React Flow canvas; drag/drop/connect/configure

Definition of Done: Visual workflow creation

## S8 — Builder Integration

Tasks: Serialize/save/load/validate/run workflow JSON

Definition of Done: No-code workflow executes

## S9 — Tools

Tasks: Calculator, file reader/writer, PDF reader, web search

Definition of Done: Useful tool-enabled agents

## S10 — Tool Calling

Tasks: AI tool selection, schemas, results, permissions

Definition of Done: AI can call tools

## S11 — Memory + RAG

Tasks: Conversation memory, facts, document chunks, vector search

Definition of Done: Document-aware agents

## S12 — Autonomous Agent

Tasks: Goal/planning/action/observation loop, limits, approvals

Definition of Done: Multi-step autonomous execution

## S13 — Security

Tasks: File/tool permissions, shell restrictions, audit logs

Definition of Done: Controlled sensitive actions

## S14 — Offline

Tasks: Online/offline/auto routing; local model + local tools

Definition of Done: Core offline agent scenario

## S15 — Templates

Tasks: Research, Document, Coding, Assistant; import/export

Definition of Done: Easy onboarding

## S16 — Release

Tasks: QA, logging, installer, docs, beta fixes

Definition of Done: MVP Windows beta

# 11. MVP Acceptance Criteria

User can install the Windows application.

User can select a local model and chat without internet.

User can create an agent without writing code.

User can drag, connect and configure workflow nodes.

User can save and reload workflows.

Agent can call at least five tools.

Agent has conversation and document memory.

Run history shows each workflow step and errors.

Sensitive actions use explicit permissions.

Offline mode works with local model, local files and local memory.

User can export/import an agent workflow.

# 12. Development Rules

Build one vertical slice at a time and finish every sprint with something runnable.

Keep the agent engine independent from the desktop UI.

Use deterministic workflows before adding autonomous planning.

Treat file, shell and internet access as permission-controlled capabilities.

Prefer local execution for privacy and offline use; make cloud models optional.

Do not build the marketplace, Android app or advanced collaboration until the Windows MVP is stable.

# 13. Major Milestones

M1 — Local Chat: Windows → Local LLM → Answer

M2 — First Agent: Input → AI → Output

M3 — No-Code Agent: Drag → Connect → Run

M4 — Tool Agent: AI → Tool → AI

M5 — Memory Agent: Agent → Memory → Recall

M6 — Offline Agent: no internet but local model/tools/memory

M7 — Autonomous Agent: Goal → Plan → Tools → Result

M8 — AI Workflow Builder: Natural language → Workflow → Approval → Run