## Sprint Backlog
Sprint | Epic | Area | Priority | Task / User Story | Acceptance Criteria | Status | Story Points | Owner | Dependencies
S1 | Foundation | Desktop | P0 | Create Tauri + React Windows shell | App opens and navigation works | Backlog | 5 |  |  | Done
S1 | Foundation | Backend | P0 | Create FastAPI service | /health returns OK | Backlog | 3
S1 | Foundation | Repository | P0 | Create Git/GitHub structure | Repo, README and branches ready | Backlog | 2
S2 | Foundation | Database | P0 | Create SQLite schema | Core tables created and tested | Backlog | 5 |  | S1
S2 | Foundation | Agent CRUD | P0 | Create agent CRUD APIs/UI | Create/edit/delete/list works | Backlog | 8 |  | S2 database
S3 | Local AI | Ollama | P0 | Integrate Ollama | Local model returns output | Backlog | 8 |  | S1
S3 | Local AI | Chat | P0 | Build local chat UI | User can chat with local model | Backlog | 5 |  | Ollama
S4 | Local AI | Abstraction | P0 | Create ModelProvider interface | Engine calls provider through common interface | Backlog | 5 |  | S3
S4 | Local AI | Cloud | P1 | Add first cloud provider adapter | Cloud model can be selected and invoked | Backlog | 5 |  | S4 interface
S5 | Agent Engine | Runtime | P0 | Implement workflow runtime | Trigger→AI→Output executes | Backlog | 8 |  | S2,S4
S5 | Agent Engine | Context | P0 | Implement execution context | Inputs/variables/outputs persist during run | Backlog | 5 |  | Runtime
S6 | Agent Engine | Logic | P0 | Add condition and branching | TRUE/FALSE paths execute correctly | Backlog | 5 |  | S5
S6 | Agent Engine | Reliability | P0 | Add retries/timeouts/run-step logs | Failed node is visible with error | Backlog | 5 |  | S5
S7 | Builder | Canvas | P0 | Build React Flow editor | Nodes can be dragged and connected | Backlog | 8 |  | S5
S7 | Builder | Node Library | P0 | Create initial node library | Trigger/AI/Tool/Logic/Output available | Backlog | 5 |  | Canvas
S8 | Builder | Persistence | P0 | Save/load workflow JSON | Workflow reloads correctly | Backlog | 5 |  | S2,S7
S8 | Builder | Execution | P0 | Run workflow from builder | Visual workflow executes through backend | Backlog | 8 |  | S6,S8
S9 | Tools | Core | P0 | Calculator + file read/write | Tools work independently and via agent | Backlog | 8 |  | S6
S9 | Tools | Documents | P1 | PDF text extraction | Agent can read PDF text | Backlog | 5 |  | Core tools
S9 | Tools | Web | P1 | Web search tool | Search returns structured results | Backlog | 5 |  | Permissions
S10 | Tools | Tool Calling | P0 | AI selects and calls tools | AI chooses tool, receives result and continues | Backlog | 8 |  | S9
S10 | Tools | Permissions | P0 | Tool permission framework | Sensitive calls can be approved/denied | Backlog | 5 |  | S9
S11 | Memory | Conversation | P1 | Persist conversation memory | Agent retrieves recent conversation | Backlog | 5 |  | S2
S11 | Memory | RAG | P1 | Document embeddings/vector search | Relevant chunks are retrieved | Backlog | 8 |  | PDF tool
S12 | Autonomous | Planner | P1 | Implement goal/action loop | Agent executes multiple steps | Backlog | 8 |  | S10,S11
S12 | Autonomous | Safety | P0 | Step limit + timeout + approval | Agent cannot run indefinitely | Backlog | 5 |  | Planner
S13 | Security | Permissions | P0 | Restrict file/tool access | Only approved capabilities are available | Backlog | 8 |  | S10
S13 | Security | Audit | P1 | Record sensitive actions | Actions appear in run history | Backlog | 5 |  | S6
S14 | Offline | Routing | P0 | Implement online/offline/auto modes | Offline blocks cloud/internet tools | Backlog | 5 |  | S4,S10
S14 | Offline | Readiness | P0 | Verify local model + memory + files | Core offline scenario succeeds | Backlog | 5 |  | S11
S15 | Templates | Templates | P1 | Create five agent templates | Templates can be copied and run | Backlog | 8 |  | S14
S15 | Templates | Import/Export | P1 | Export/import .agent.json | Agent transfers between installations | Backlog | 5 |  | S8
S16 | Release | Packaging | P0 | Build Windows installer | Fresh installation succeeds | Backlog | 5 |  | Core epics
S16 | Release | QA | P0 | Run end-to-end regression | Critical workflows pass | Backlog | 8 |  | Core epics
S16 | Release | Docs | P1 | Create user/developer docs | Install and agent creation documented | Backlog | 3 |  | Packaging

## Sprint Overview
Sprint | Epic | Goal | Duration | Planned SP | Status | Review Outcome
S1 | Foundation | Windows shell + backend foundation | 2 weeks | 10 | Not Started | Runnable desktop shell
S2 | Foundation | SQLite + agent CRUD | 2 weeks | 13 | Not Started | Create/manage agents
S3 | Local AI | Ollama + local chat | 2 weeks | 13 | Not Started | Offline local chat
S4 | Local AI | Model abstraction + cloud adapter | 2 weeks | 10 | Not Started | Switchable model providers
S5 | Agent Engine | Basic workflow runtime | 2 weeks | 13 | Not Started | First executable agent
S6 | Agent Engine | Logic + reliability | 2 weeks | 10 | Not Started | Multi-step workflow engine
S7 | Builder | Visual workflow editor | 2 weeks | 13 | Not Started | Drag/drop builder
S8 | Builder | Builder-to-engine integration | 2 weeks | 13 | Not Started | No-code workflow runs
S9 | Tools | Core tools | 2 weeks | 18 | Not Started | Useful tool-enabled agents
S10 | Tools | Tool calling + permissions | 2 weeks | 13 | Not Started | AI chooses tools
S11 | Memory | Memory + RAG | 2 weeks | 13 | Not Started | Document-aware agent
S12 | Autonomous | Planning/action loop | 2 weeks | 13 | Not Started | Multi-step autonomous agent
S13 | Security | Permissions + audit | 2 weeks | 13 | Not Started | Controlled sensitive actions
S14 | Offline | Offline mode | 2 weeks | 10 | Not Started | Offline agent scenario
S15 | Templates | Templates + import/export | 2 weeks | 13 | Not Started | Easy onboarding
S16 | Release | QA + Windows release | 2 weeks | 16 | Not Started | MVP beta

## Agile Board
Task ID | Sprint | Task | Status | Priority | Story Points | Owner
AG-001 | S1 | Create Tauri + React Windows shell | Backlog | P0 | 5 | Monish
AG-002 | S1 | Create FastAPI service | Backlog | P0 | 3
AG-003 | S1 | Create Git/GitHub structure | Backlog | P0 | 2
AG-004 | S2 | Create SQLite schema | Backlog | P0 | 5
AG-005 | S2 | Create agent CRUD APIs/UI | Backlog | P0 | 8
AG-006 | S3 | Integrate Ollama | Backlog | P0 | 8
AG-007 | S3 | Build local chat UI | Backlog | P0 | 5
AG-008 | S4 | Create ModelProvider interface | Backlog | P0 | 5
AG-009 | S4 | Add first cloud provider adapter | Backlog | P1 | 5
AG-010 | S5 | Implement workflow runtime | Backlog | P0 | 8
AG-011 | S5 | Implement execution context | Backlog | P0 | 5
AG-012 | S6 | Add condition and branching | Backlog | P0 | 5
AG-013 | S6 | Add retries/timeouts/run-step logs | Backlog | P0 | 5
AG-014 | S7 | Build React Flow editor | Backlog | P0 | 8
AG-015 | S7 | Create initial node library | Backlog | P0 | 5
AG-016 | S8 | Save/load workflow JSON | Backlog | P0 | 5
AG-017 | S8 | Run workflow from builder | Backlog | P0 | 8
AG-018 | S9 | Calculator + file read/write | Backlog | P0 | 8
AG-019 | S9 | PDF text extraction | Backlog | P1 | 5
AG-020 | S9 | Web search tool | Backlog | P1 | 5
AG-021 | S10 | AI selects and calls tools | Backlog | P0 | 8
AG-022 | S10 | Tool permission framework | Backlog | P0 | 5
AG-023 | S11 | Persist conversation memory | Backlog | P1 | 5
AG-024 | S11 | Document embeddings/vector search | Backlog | P1 | 8
AG-025 | S12 | Implement goal/action loop | Backlog | P1 | 8
AG-026 | S12 | Step limit + timeout + approval | Backlog | P0 | 5
AG-027 | S13 | Restrict file/tool access | Backlog | P0 | 8
AG-028 | S13 | Record sensitive actions | Backlog | P1 | 5
AG-029 | S14 | Implement online/offline/auto modes | Backlog | P0 | 5
AG-030 | S14 | Verify local model + memory + files | Backlog | P0 | 5
AG-031 | S15 | Create five agent templates | Backlog | P1 | 8
AG-032 | S15 | Export/import .agent.json | Backlog | P1 | 5
AG-033 | S16 | Build Windows installer | Backlog | P0 | 5
AG-034 | S16 | Run end-to-end regression | Backlog | P0 | 8
AG-035 | S16 | Create user/developer docs | Backlog | P1 | 3

## Definition of Done
Area | Definition
Code | Acceptance criteria implemented
Review | Code reviewed and merged
Testing | Relevant unit/integration tests pass
Security | Secrets and permissions checked
UX | Loading/error/empty states handled
Documentation | Feature docs updated
Demo | Feature demonstrated in working build
Regression | Critical existing workflows still pass

## Priority Guide
Priority | Meaning | Examples
P0 | Must have for MVP | Agent engine, builder, local AI, core tools
P1 | Important after core | RAG, autonomous planning, cloud providers, templates
P2 | Nice to have | Advanced integrations and analytics
P3 | Later | Marketplace, collaboration, Android client